Meeting Agenda with Dean Galea — 2 October 2026

# Active manuscripts

| # | Manuscript | Stage | Target journal | Next step | Due |
| --- | --- | --- | --- | --- | --- |
| 1 | MaRVIN 1 — Validation of Mental Health Screening Instruments in Nigerian Populations | In proof stage (copy edit returned to JTS) | Journal of Traumatic Stress | Awaiting page proofs for final author review before publication | ~Oct 7 |
| 2 | Commercial Determinants of Armed Conflict and the Global Arms Industry | Revised and resubmitted (Oct 1); acknowledged by the journal | WHO Bulletin | Awaiting editorial decision | ~Oct 1 (CDoH theme issue) — met |
| 3 | Digital Environments as Health Environments: Reframing Digital Health for Population Health | Revise & resubmit received (Sep 17); two external reviews | SSM-Population Health | Revise per reviewers (study-selection/method transparency, justification of the five domains and mechanisms, non-US/LMIC evidence, concrete measures and study designs, governance tensions and feasibility, reference cleanup); point-by-point response | Oct 8, 2026 |
| 4 | MaRVIN Burden paper — Trauma, Displacement, and Common Mental Disorders in Populations Exposed to Ongoing High-Prevalence Violence | With co-authors | JAMA NO / BMJ Global Health | Nudge co-authors |  |
| 5 | MaRVIN Stress/Trauma — Trauma-Stress Interactions and Mental Health Outcomes in Nigeria | Draft 1 | Social Science & Medicine | Finalize draft |  |
| 6 | MaRVIN Expanded validation (population-level validation of PCL-5, PHQ-9, GAD-7) | Phase 2 outline shared with Gavin (Sep 14); aligned at meeting | TBD | Begin drafting per outline |  |
| 7 | MaRVIN TMDS instrument | Outline 3 | TBD | Reframe intro; reproduce Outline 3 |  |
| 8 | "Increasing Defence Expenditure May Cost Us Our Security" (Mohammed Abba-Aji, Nason Maani) | Accepted; COI declarations complete, with BMJ's technical editor for production | The BMJ (climate issue) | Awaiting proofs from the technical editor |  |
| 9 | Digital Determinants of Health Viewpoint (with Jay Shaw) | Revised outline in from Jay; Sandro reviewed with suggestions | JAMA Health Forum | Draft next (Jay leading, per his Sep 24 note) |  |

# On hold

| # | Manuscript | Stage | Target journal | Next step |
| --- | --- | --- | --- | --- |
| 1 | Modelling the Role of Serious Mental Illness in Interpersonal Gun Violence: A Population Health Perspective | Revise & resubmit | SSM-Population Health | Redo analysis |
| 2 | Trends in Undiagnosed Hypertension Among US Adults, 1999-2000 Through 2017-2018 (NHANES) | Outline 2 | TBD | Pending active items; RA support onboarding for citations |
| 3 | Sociodemographic Differences in Undiagnosed, Untreated and Uncontrolled Hypertension Among US Adults (NHANES) | Outline 2 | TBD | Pending active items |
| 4 | PHC Mental Healthcare Services Readiness Assessment | Concept note | TBD | Discuss scope; revise concept note |
| 5 | Psychological Distress (Gavin) | Outline 2 | TBD | Revise concept note |
| 6 | Mental Health Indicators and Gun Purchase Intentions | With Salma | SSM-Mental Health | Send to co-authors |
| 7 | Trends and Sociodemographic Predictors in Cannabis Positivity Among Adolescent Homicide Decedents, 2009-2022 | Outline 3 refining | JAMA Pediatrics / Psychiatry | Send to Sandro |
| 8 | Impact of Cannabis Retail Legalization on Cannabis Positivity Among Adolescent Homicide Decedents, 2009-2022 | Outline 2 refining | JAMA Pediatrics / Psychiatry | Outline 3 |
| 9 | Food Insecurity and Mental Health (Bella) | Outline 2 | TBD | Intro to Epi study; Outline 3 |

# Projects

| # | Project | Updates | Next step |
| --- | --- | --- | --- |
| 1 | AI and Public Health Survey | National survey of AI in public health practice; leading with Brownson's support, Jen Layden joined. Framed as an adoption study: individual use mapped to Shah's three tiers with a sanctioned / tolerated / unsanctioned item, ASTHO challenge categories, local health departments included. Met with Layden and Brownson Oct 1 — discussed next steps, presented the plan | Layden and Brownson to reach out separately to ASTHO and NACCHO; concept note to follow |
| 2 | Annual PH&S Lecture and book event | PH&S confirms funding for 100 copies; School covers 100; books have arrived, and an A/V team will be on site | [date and format] bracket still open |
| 3 | Epidemiology Matters | Four external reviews received; response letter drafted in the Zimmerman format; approved by Kerry and sent to Emma at OUP | Meeting with Kerry for next steps |
| 4 | St. Louis SHINE Survey | NORC sent incentive proposal; Morven following up; no meeting needed this week | Pilot data collection |
| 5 | MaRVIN dissertation on primary care implementation in Nigeria | Saidat and Jaimie shaping dissertation | Committee; timelines |
| 6 | MaRVIN Second Wave | Met with AFENET; participant recruitment and cost | Awaiting budget / revisions |
| 7 | Rural Health Task Force | White paper drafting underway; writing assignments distributed | Updating analysis with new data; drafting part of the landscape report |
| 8 | AI & Digital Innovation in Public Health Curriculum (MPH) | Kick-off meeting held | Course concept |
| 9 | Lancet Global Gun Violence Commission | Working-group synthesis completed; feedback received this week | Meeting with Aisha next week for next steps |

# Training

| # | Training | Status | Next step |
| --- | --- | --- | --- |
| 1 | Teaching with AI series (Eddie Watson, FRPHC course developer team) | First session attended; four one-hour sessions to follow this academic year | Dates set (Hobson, Sep 17): Oct 6 2-4, Oct 20 1-3, Oct 23 9-11, Oct 28 2-4, Nov 20 10-12, Dec 4 10-12; Tish sending hybrid invites |