# Weekly Updates — Week of 19 October – 23 October, 2026

## Active manuscripts

| # | Manuscript | Stage | Target journal | Next step | Due |
| --- | --- | --- | --- | --- | --- |
| 1 | MaRVIN 1 — Validation of Mental Health Screening Instruments in Nigerian Populations | Page proofs received (Oct 22) | Journal of Traumatic Stress | Return proofs for final author review before publication |  |
| 2 | Commercial Determinants of Armed Conflict and the Global Arms Industry | Accepted (Oct 19) | WHO Bulletin | Edited version for approval within a month (2-day turnaround) |  |
| 3 | Digital Environments as Health Environments: Reframing Digital Health for Population Health | Revise & resubmit received (Sep 17); two external reviews | SSM-Population Health | Revise per reviewers point-by-point response | Nov 12, 2026 |
| 4 | MaRVIN Burden paper — Trauma, Displacement, and Common Mental Disorders in Populations Exposed to Ongoing High-Prevalence Violence | With co-authors | JAMA NO / BMJ Global Health | Nudge co-authors |  |
| 5 | MaRVIN Stress/Trauma — Trauma-Stress Interactions and Mental Health Outcomes in Nigeria | Draft 1 | Social Science & Medicine | Finalize draft |  |
| 6 | MaRVIN Expanded validation (population-level validation of PCL-5, PHQ-9, GAD-7) | Drafting with Gavin; Introduction and Discussion edits in (Oct 16) | TBD | Review Gavin's edits |  |
| 7 | MaRVIN TMDS instrument | Outline 3 | TBD | Reframe intro; reproduce Outline 3 |  |
| 8 | "Increasing Defence Expenditure May Cost Us Our Security" (Mohammed Abba-Aji, Nason Maani) | Published online Oct 21 in the BMJ climate issue, with a BMJ press release | The BMJ (climate issue) | BMJ podcast recorded with Neta Crawford (Oct 22); Earth.com story in preparation |  |
| 9 | Digital Determinants of Health Viewpoint (with Jay Shaw) | Revised outline in from Jay; Sandro reviewed with suggestions | JAMA Health Forum | Draft next (Jay leading, per his Sep 24 note) |  |

## Teaching and Mentorship

| # | Item | Updates | Next step |
| --- | --- | --- | --- |
| 1 | PHS1000 (Foundations in Public Health) | Midterm graded; Salma Abdalla guest lecture on social and structural determinants (Oct 13); Lab III on systems thinking (Oct 15) | Patrick Aguilar guest lecture (Oct 29) |
| 2 | RA / TA mentoring pipeline | Group-training session outlined for Parth, Ellie, Gabriel Estrada, Zoe; Zoe Rochester to TA Intro to Epi in spring | Send the RA group-training email |

## Projects

| # | Project | Updates | Next step |
| --- | --- | --- | --- |
| 1 | AI and Public Health Survey | National survey of AI in public health practice; leading with Brownson's support, Jen Layden joined. PH WINS (de Beaumont) meeting being scheduled | Meeting with ASTHO secured |
| 2 | Annual PH&S Lecture and book event | PH&S confirms books have arrived, and an A/V team will be on site | None |
| 3 | Epidemiology Matters | Response letter with OUP | Meeting with Kerry for next steps |
| 4 | St. Louis SHINE Survey | Soft launch fielded and data shared (Oct 15); NORC confirmed timing for the first ABS invitation mailing (Oct 21) | Data check, then full launch |
| 5 | MaRVIN dissertation on primary care implementation in Nigeria | Saidat and Jaimie shaping dissertation | Committee; timelines |
| 6 | MaRVIN Second Wave | Met with AFENET; participant recruitment and cost | Awaiting budget / revisions |
| 7 | Rural Health Task Force | White paper drafted; Morven consolidating contributions, edits paused (Oct 21) | White paper sent to Dean Galea. |
| 8 | AI & Digital Innovation in Public Health Curriculum (MPH) | Course pitch meeting held; presentation to the MPH Education Subcommittee set for Nov 30 | Course syllabus and proposal (due Nov 23) |
| 9 | Lancet Global Gun Violence Commission | Working-group synthesis completed; met Aisha (Oct 13) on the feedback | [next steps agreed with Aisha] |
| 10 | Public Health 3rd edition (Springer) | Met Springer's digital team (Oct 16) | Map the modular structure with Angela and Jim |

## Training

| # | Training | Status | Next step |
| --- | --- | --- | --- |
| 1 | Teaching with AI series (Eddie Watson, FRPHC course developer team) | Sessions ongoing; next on Oct 20 and Oct 23 | Meeting and training sessions. |
| 2 | MIT Applied AI and Data Science Program | Registered; preparatory sessions under way; live course starts Nov 21 | Pre-course training from now to Nov 21 |

## On hold

| # | Manuscript | Stage | Target journal | Next step |
| --- | --- | --- | --- | --- |
| 1 | Modelling the Role of Serious Mental Illness in Interpersonal Gun Violence: A Population Health Perspective | Revise & resubmit | SSM-Population Health | Redo analysis |
| 2 | Trends in Undiagnosed Hypertension Among US Adults, 1999-2000 Through 2017-2018 (NHANES) | Outline 2 | TBD | Pending active items; RA support onboarding for citations |
| 3 | Sociodemographic Differences in Undiagnosed, Untreated and Uncontrolled Hypertension Among US Adults (NHANES) | Outline 2 | TBD | Pending active items |
| 4 | PHC Mental Healthcare Services Readiness Assessment | Concept note | TBD | Discuss scope; revise concept note |
| 5 | Psychological Distress (Gavin) | Outline 2 | TBD | Revise concept note |
| 6 | Mental Health Indicators and Gun Purchase Intentions | With Salma | SSM-Mental Health | Send to co-authors |
| 7 | Trends and Sociodemographic Predictors in Cannabis Positivity Among Adolescent Homicide Decedents, 2009-2022 | Outline 3 refining | JAMA Pediatrics / Psychiatry | Send to Sandro |
| 8 | Impact of Cannabis Retail Legalization on Cannabis Positivity Among Adolescent Homicide Decedents, 2009-2022 | Outline 2 refining | JAMA Pediatrics / Psychiatry | Outline 3 |
| 9 | Food Insecurity and Mental Health (Bella) | Outline 2 | TBD | Intro to Epi study; Outline 3 |